VnComply

CONDENSED TASK LIST — DEMO SPRINT

Privacy Compliance + Web Security Assessment Platform

Deadline: 25/4/2026  |  Stack: Python · Playwright · Next.js · SQLite · Docker

⚠️ Ngữ cảnh: Timeline bị rút ngắn → ưu tiên tuyệt đối 4 tính năng core để đảm bảo demo chất lượng cao nhất. Mọi task không ảnh hưởng trực tiếp đến demo flow bị CẮT hoặc DỜI POST-DEMO.

🎯 4 TÍNH NĂNG CORE CẦN HOÀN THÀNH

| # | Tính năng | Mô tả cốt lõi | Output demo |
| --- | --- | --- | --- |
| F1 | Privacy / Policy Scanner | Quét cookie consent, third-party tracker, pre-consent tracking theo Nghị định 13/2023 & GDPR | Danh sách vi phạm có mức độ |
| F2 | Demo Target Web | Web tự build có lỗ hổng cố ý: SQLi, XSS, CSRF, weak auth, no consent banner | URL live để scan |
| F3 | OWASP Top 10 Scanner | Tự động phát hiện 10 lớp lỗ hổng bảo mật theo OWASP | Finding list + severity |
| F4 | Report Export | Xuất báo cáo tổng hợp Privacy + Security dạng HTML & PDF | File tải về được |

📅 TIMELINE TỔNG QUAN (18 ngày)

| Phase | Tên | Nội dung chính | Timeline |
| --- | --- | --- | --- |
| P1 | Foundation | Docker, FastAPI, SQLite schema, Auth JWT | 7–8/4 (2 ngày) |
| P2 | Demo Target Web | Vulnerable web app (Next.js + FastAPI) | 9–11/4 (3 ngày) |
| P3 | Privacy Scanner | Playwright crawler, cookie, tracker | 12–15/4 (4 ngày) |
| P4 | OWASP Scanner | SQLi, XSS, CSRF, Headers, Secrets… | 16–20/4 (5 ngày) |
| P5 | Report Engine | HTML + PDF report, scoring, export | 21–23/4 (3 ngày) |
| P6 | Demo Polish | UI flow, end-to-end test, buffer | 24–25/4 (2 ngày) |

🛠️ TECH STACK ĐÃ TỐI GIẢN

| Layer | Công nghệ | Vai trò |
| --- | --- | --- |
| Backend API | FastAPI (Python) | Scanner engine, REST API, auth JWT, job queue |
| Browser Engine | Playwright | Privacy crawl, cookie/tracker detection, screenshots |
| Frontend | Next.js / React | Dashboard UI, scan config, live progress, report viewer |
| Database | SQLite | Scan jobs, findings, reports – zero-config, demo-ready |
| Container | Docker Compose | 1-command spin-up toàn bộ stack (API + Web + DB) |
| HTTP Client | httpx + BeautifulSoup | OWASP payload testing, header analysis, link crawl |
| Report Export | Jinja2 + WeasyPrint | HTML template → PDF export chuyên nghiệp |
| Target Web | Next.js + FastAPI | Vulnerable demo app (cố ý có lỗ hổng để scan) |

Đã cắt: Redis, Celery, PostgreSQL (→ SQLite), Kong API Gateway, RBAC phức tạp (→ simple JWT), CI/CD pipeline, WebSocket real-time, TOTP 2FA, SSO OAuth. Tất cả có thể bổ sung post-demo.

PHASE 1 — Foundation (7–8/4) · 2 ngày

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Khởi tạo Docker Compose (FastAPI + Next.js + SQLite volumes) | 🔴 MUST | 4h | Docker | ☐ |
| 1.2 | Tạo database schema SQLite: scans, findings, reports, users | 🔴 MUST | 3h | SQLite | ☐ |
| 1.3 | API auth JWT: đăng ký / đăng nhập / middleware bảo vệ route | 🔴 MUST | 4h | FastAPI | ☐ |
| 1.4 | Background job runner đơn giản (asyncio task queue – không cần Redis) | 🔴 MUST | 3h | Python asyncio | ☐ |
| 1.5 | Next.js boilerplate: layout, auth pages, dashboard skeleton | 🔴 MUST | 4h | Next.js | ☐ |

PHASE 2 — Demo Target Web (9–11/4) · 3 ngày

Mục tiêu P2: Xây dựng 1 web app 'nạn nhân' có lỗ hổng CỐ Ý để scanner của mình có thể detect và demo live. Chạy trong Docker cùng stack.

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Next.js frontend: trang đăng nhập, đăng ký, profile, admin panel (có lỗ hổng) | 🔴 MUST | 6h | Next.js | ☐ |
| 2.2 | FastAPI backend: endpoint có SQLi (raw query), XSS (reflected), no input sanitize | 🔴 MUST | 5h | FastAPI | ☐ |
| 2.3 | Cố ý thiếu: CSRF token, SameSite cookie, security headers (X-Frame, CSP, HSTS) | 🔴 MUST | 2h | FastAPI | ☐ |
| 2.4 | Cố ý thiếu: cookie consent banner, Google Analytics load trước consent | 🔴 MUST | 2h | Next.js | ☐ |
| 2.5 | Để lộ: .env endpoint, debug stacktrace, weak JWT secret (HS256 + 'secret') | 🟡 HIGH | 2h | FastAPI | ☐ |
| 2.6 | IDOR bug: /api/users/{id} không check ownership → truy cập data user khác | 🟡 HIGH | 2h | FastAPI | ☐ |
| 2.7 | Deploy target web lên Docker, verify accessible từ scanner service | 🔴 MUST | 1h | Docker | ☐ |

PHASE 3 — Privacy / Policy Scanner (12–15/4) · 4 ngày

Pháp lý áp dụng: Nghị định 13/2023/NĐ-CP (Điều 9, 11, 15, 17) + GDPR Article 7 (Consent) + ePrivacy Directive (Cookie Law)

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Playwright crawler: navigate → networkidle → intercept requests có timestamp ms | 🔴 MUST | 5h | Playwright | ☐ |
| 3.2 | Cookie consent detector: scan DOM tìm banner, CMP (OneTrust, Cookiebot), nút Accept/Reject | 🔴 MUST | 5h | Playwright | ☐ |
| 3.3 | Pre-consent tracking: so sánh timestamp request vs timestamp click Accept → vi phạm NĐ13 | 🔴 MUST | 5h | Python | ☐ |
| 3.4 | Third-party tracker classifier: phân loại domain → Analytics / Ads / Social / Functional | 🔴 MUST | 4h | Python | ☐ |
| 3.5 | Consent compliance checks: pre-checked box, bundled consent, missing reject button | 🟡 HIGH | 4h | Playwright | ☐ |
| 3.6 | SSL/TLS check: version, expiry, self-signed, HSTS header | 🟡 HIGH | 2h | httpx | ☐ |
| 3.7 | Lưu findings vào SQLite: violation_type, severity, url, evidence, screenshot path | 🔴 MUST | 2h | SQLite | ☐ |
| 3.8 | API endpoint: POST /scans/privacy, GET /scans/{id}/status, GET /scans/{id}/findings | 🔴 MUST | 3h | FastAPI | ☐ |

PHASE 4 — OWASP Top 10 Scanner (16–20/4) · 5 ngày

Phạm vi: 10 category OWASP Top 10:2021. Mỗi category có ít nhất 1 detection có thể trigger trên demo target web → đảm bảo demo live.

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 4.1 | A01 – Broken Access Control: IDOR check (thay ID trong URL), path traversal, admin endpoint exposure | 🔴 MUST | 5h | httpx | ☐ |
| 4.2 | A02 – Cryptographic Failures: detect HTTP (no HTTPS), weak TLS, sensitive data in response (passwords, keys) | 🔴 MUST | 4h | httpx | ☐ |
| 4.3 | A03 – Injection (SQLi + XSS): inject payloads vào form fields & URL params, detect error / reflection | 🔴 MUST | 6h | Python | ☐ |
| 4.4 | A04 – Insecure Design: detect exposed debug endpoints (/debug, /.env, /api/docs không auth) | 🟡 HIGH | 3h | httpx | ☐ |
| 4.5 | A05 – Security Misconfiguration: check missing security headers (CSP, HSTS, X-Frame, X-Content-Type) | 🔴 MUST | 3h | httpx | ☐ |
| 4.6 | A06 – Vulnerable Components: extract JS libs từ HTML (jQuery, React version), check CVE list cục bộ | 🟡 HIGH | 4h | BeautifulSoup | ☐ |
| 4.7 | A07 – Auth Failures: brute-force check (rate limit?), weak session cookie flags, JWT weak secret detection | 🔴 MUST | 4h | httpx | ☐ |
| 4.8 | A08 – Software Integrity: check subresource integrity (SRI) trên CDN scripts | 🟢 NICE | 2h | BeautifulSoup | ☐ |
| 4.9 | A09 – Logging Failures: phát hiện stack trace / verbose error trong response body | 🟡 HIGH | 2h | Python | ☐ |
| 4.10 | A10 – SSRF: test URL input fields với internal IP (127.0.0.1, 169.254.169.254), check response diff | 🟡 HIGH | 3h | httpx | ☐ |
| 4.11 | CSRF check: kiểm tra form có CSRF token không, SameSite cookie attribute | 🔴 MUST | 2h | Playwright | ☐ |
| 4.12 | Lưu security findings vào SQLite: owasp_category, cvss_score, payload, request, response, severity | 🔴 MUST | 2h | SQLite | ☐ |
| 4.13 | API endpoint: POST /scans/security, GET /scans/{id}/owasp-findings | 🔴 MUST | 2h | FastAPI | ☐ |

PHASE 5 — Report Engine (21–23/4) · 3 ngày

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Jinja2 HTML template: Executive Summary, Privacy Violations, OWASP Findings, Risk Matrix | 🔴 MUST | 6h | Jinja2 | ☐ |
| 5.2 | Scoring engine: Privacy score (0-100) + Security score (0-100) + Overall posture | 🔴 MUST | 3h | Python | ☐ |
| 5.3 | PDF export: WeasyPrint render HTML → PDF (logo, color, table, charts) | 🔴 MUST | 4h | WeasyPrint | ☐ |
| 5.4 | Compliance mapping table: findings → NĐ13/2023 điều khoản + OWASP Top 10 category | 🟡 HIGH | 3h | Python | ☐ |
| 5.5 | API endpoint: GET /reports/{scan_id}/html, GET /reports/{scan_id}/pdf | 🔴 MUST | 2h | FastAPI | ☐ |
| 5.6 | Next.js report viewer: hiển thị findings có filter theo severity, download PDF button | 🔴 MUST | 4h | Next.js | ☐ |

PHASE 6 — Demo Polish (24–25/4) · 2 ngày

| ID | Task | Ưu tiên | Ước tính | Công nghệ | Done |
| --- | --- | --- | --- | --- | --- |
| 6.1 | End-to-end demo flow test: launch scan → live progress → findings → download PDF | 🔴 MUST | 4h | Manual | ☐ |
| 6.2 | UI polish dashboard: scan progress bar, severity badges, finding cards, score gauge | 🟡 HIGH | 5h | Next.js | ☐ |
| 6.3 | Chuẩn bị demo script: URL target, expected findings, expected report output | 🔴 MUST | 2h | Docs | ☐ |
| 6.4 | Docker Compose production build: verify 1-command startup từ đầu | 🔴 MUST | 2h | Docker | ☐ |
| 6.5 | Buffer: fix bugs phát sinh từ E2E test | 🔴 MUST | 3h | All | ☐ |

🚫 ĐÃ CẮT (POST-DEMO)

| Đã cắt | Lý do / Thay thế |
| --- | --- |
| RBAC 6 vai trò phức tạp | → Dùng simple JWT, 1 admin role. RBAC bổ sung sau. |
| Redis + Celery task queue | → Dùng Python asyncio đơn giản. Đủ cho demo 1 scan tại thời điểm. |
| PostgreSQL | → SQLite. Zero-config, zero-setup, sufficient for demo data volume. |
| CI/CD pipeline (GitHub Actions) | → Docker Compose thủ công. Đủ cho demo. |
| WebSocket real-time progress | → Polling đơn giản mỗi 3 giây từ frontend. |
| TOTP 2FA + SSO OAuth | → Chỉ giữ JWT. 2FA/SSO bổ sung post-demo. |
| WAF bypass testing module | → Không có WAF trên demo target → không applicable. |
| API Security Testing (GraphQL…) | → Chỉ test REST endpoints cơ bản. GraphQL/WebSocket sau. |
| Continuous monitoring / scheduler | → Không cần cho 1-time demo. On-demand scan là đủ. |
| DNS security, port scanning | → Out of scope cho demo web app. |
| Audit logs đầy đủ | → Chỉ log scan events cơ bản trong SQLite. |

📊 TÓM TẮT EFFORT

| Phase | Tên | Tasks | Est. Hours | Deadline |
| --- | --- | --- | --- | --- |
| P1 | Foundation | 5 | 18h | 8/4 |
| P2 | Demo Web | 7 | 20h | 11/4 |
| P3 | Privacy Scanner | 8 | 30h | 15/4 |
| P4 | OWASP Scanner | 13 | 42h | 20/4 |
| P5 | Report Engine | 6 | 22h | 23/4 |
| P6 | Demo Polish | 5 | 16h | 25/4 |
| — | TOTAL | 44 | ~148h | 25/4 ✅ |

💡 Ghi chú: ~148h trong 18 ngày = ~8.2h/ngày. Khả thi cho solo dev nếu focus tuyệt đối. Task 🟢 NICE có thể skip nếu thời gian tight. Priority: MUST trước, HIGH nếu còn thời gian.